## V1
Project Development and Completion Tracker
Project Start Date: 01-07-2023 Project End Date: 31-10-23
Group ID: 07
Porject Descreption: Analysis and apllication of different machine learning algorithms using cancer diagnosis dataset
Guide Name: Prof. Shahin Makubhai
| Name of Team member | Enrollment
Project Team Members | Harshal Jadhav | MITU20BTCS0111
| Pranav Deshpande | MITU20BTCS0199
| Rohit Khare | MITU20BTCS0236
Epic: | As a Medical expert, I should know the best algorithm available in the market to analyze cancer diagnosis rates in world
Story 1: | As a medical expert, I should know different algorithms of machine learning
Story 2: | As a medical expert, I should know the rates of cancer detection and espacially early cancer diagnosis in overall world
Story 3: | As a medical expert, I need reccomendation of best algorithm among the algorithms available in the field of machine leaning
Task1: | Seeking different and most relatable cancer dataset available on internet
Task2: | Setting up enviornment for processing the data
Task3: | Proprocessing the dataset and removing the outliers
Task4: | Calculating the accuracies and confusion matrices for each of the algorithm
Task5: | Comparing different algorithms using their accuracies, efficiencies
Acceptance Criteria:
1 | Dataset is as much relatable with the project as possible.
2 | Dataset should not be exceeding the certain limits of size.
3 | Dataset should contain as less ouliers and noice as possible.
4 | Confusion matrices an hence acuracies of the different algorithms should be calculated as output.
5 | Comparison of different algorithm with respect to the accuracies.
Sprint No. | Task Name | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Seeking different and most relatable cancer dataset available on internet | Complete | Harshal, Pranav | 2022-07-15 | 2022-07-31 | 2022-07-15 | 2022-07-31 | 100% | Not Started | Medium
| Setting up enviornment for processing the data | Complete | Harshal, Rohit | 2021-08-01 | 2022-08-31 | 2021-08-01 | 2022-08-31 | 100% | In Progress | Low
| Proprocessing the dataset and removing the outliers | Complete | All | 2021-08-01 | 2022-08-15 | 2021-08-01 | 2022-08-15 | 100% | Complete | High
Sprint 1 | Calculating the accuracies and confusion matrices for each of the algorithm | Complete | Pranav, Rohit | 2021-08-15 | 2021-09-15 | 2021-08-15 | 2021-09-15 | 100% | On Hold
| Comparing different algorithms using their accuracies, efficiencies | Complete | All | 2021-09-15 | 2023-10-15 | 2021-09-15 | 2023-10-15 | 100% | Overdue

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2