## V1
Project Development and Completion Tracker
Project Start Date: 01-07-2023 Project End Date: 20-05-24
Group ID: 07
Project Description: Cancer Detection using Machine Learning
Guide Name: Prof. Shahin Makubhai
| Name of Team member | Enrollment No.
Project Team Members | Harshal Jadhav | MITU20BTCS0111
| Pranav Deshpande | MITU20BTCS0199
| Rohit Khare | MITU20BTCS0236
Epic 1: | As a Developer, I should know the best algorithm available in the market to analyze cancer diagnosis rates in world
Story 1: | As a developer, I should know different algorithms of machine learning
Story 2: | As a developer, I should implement all the models on the dataset
Story 3: | As a developer, I should select the best possible model for the dataset
Epic 2: | As a Developer, I should develop the Explainable AI framework for the cancer diagnosis model
Story 1: | As a Developer, I should know about the different XAI frameworks available
Story 2: | As a Developer, I should implement SHAP and LIME framework with our existing algorithms
Story 3: | As a Developer, I should prepare a UI for the algorithms to display the XAI visualisation.
Task1: | Seeking different and most relatable cancer dataset available on internet
Task2: | Setting up enviornment for processing the data
Task3: | Proprocessing the dataset and removing the outliers
Task4: | Calculating the accuracies and confusion matrices for each of the algorithm
Task5: | Comparing different algorithms using their accuracies, efficiencies
Task6: | Understand about Explainable AI
Task7: | Research the various XAI libraries available.
Task8: | Implement a UI for the algorithms to display the XAI visualisation
Acceptance Criteria:
1 | Dataset is as much relatable with the project as possible.
2 | Dataset should not be exceeding the certain limits of size.
3 | Dataset should contain as less outliers and noise as possible.
4 | Comparison of different algorithm with respect to the accuracies.
Sprint No. | Task Name | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Seeking different and most relatable cancer dataset available on internet | Complete | Harshal, Pranav | 2023-07-15 | 2023-07-31 | 2023-07-15 | 2023-07-31 | 100% | Not Started | Medium
| Setting up enviornment for processing the data | Complete | Harshal, Rohit | 2023-08-01 | 2023-08-31 | 2023-08-01 | 2023-08-31 | 100% | In Progress | Low
| Proprocessing the dataset and removing the outliers | Complete | All | 2023-08-01 | 2023-08-15 | 2023-08-01 | 2023-08-15 | 100% | Complete | High
Sprint 2 | Calculating the accuracies and confusion matrices for each of the algorithm | Complete | Pranav, Rohit | 2023-15-08 | 2023-09-15 | 2023-15-08 | 2023-09-15 | 100% | On Hold
| Comparing different algorithms using their accuracies, efficiencies | Complete | All | 2023-09-15 | 2023-10-15 | 2023-09-15 | 2023-10-15 | 100% | Overdue
Sprint 3 | Implementing various XAI algorithms with exisiting ML algorithms | Complete | Rohit, Harshal | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-14 | 100%
Sprint 4 | Implement a UI for the algorithms to display the XAI visualisation | Complete | Pranav | 2024-05-11 | 2024-05-14 | 2024-05-11 | 2024-05-14 | 100%